Project Model Canvas Applied to the CMMI and MPS.Br with Support of a Tool

Simone Vasconcelos Silva
Instituto Federal Fluminense (IFFluminense)
Núcleo de Engenharia de Software (NES)
Rio de Janeiro/Brasil
simonevsinfo@gmail.com
Matheus Soares Sales
Instituto Federal Fluminense (IFFluminense)
Núcleo de Engenharia de Software (NES)
Rio de Janeiro/Brasil
matheus.soares.sales@gmail.com

Leonardo Barroso da Silva
Instituto Federal Fluminense (IFFluminense)
Núcleo de Engenharia de Software (NES)
Rio de Janeiro/Brasil
leo.barroso.silva@gmail.com

Filipe Arantes
Instituto Federal Fluminense (IFFluminense)
Núcleo de Engenharia de Software (NES)
Rio de Janeiro/Brasil
filran@gmail.com

Abstract— This article aims to propose improvements to the process of Project Management Software and is divided into four approaches that complement each other. The first provides a comparison between the processes of project management CMMI (Capability Maturity Model Integration) and MPS.Br (Improvement of Brazilian Software Process). The second presents the methodology Project Model Canvas, ie a visual methodology to facilitate collaboratively the initial development of a plan of projects with extensive interaction among stakeholders. The third proposes how Project Model Canvas can assist the implementation of the main maturity models for software presented in the first part of this work , with respect to Project Management Software. The fourth aims to present a project management tool called Integrated Management which supports the use of Project Model Canvas. This tool is based on an electronic framework with the goal of adding in one place all project documents of an organization.
Keywords—project management; maturity models; Project Model Canvas; software; Integrated Management

# I. INTRODUCTION
Currently, the effort used to develop a project plan in a traditional way is very large, whatever is the project application area. Besides that, many organizations consider the development process of the project management plan too bureaucratic. In attempt to minimize these issues, it was elaborated a methodology called Project Model Canvas, which aims to simplify the project plan conception process through a collaborative and interactive visual model among stakeholders.
This paper porpose how the Project Model Canvas methodology can add benefits to project management process of the main maturity models for software – CMMI (Capability Maturity Model Integration) and MPS.Br (Improvement of Brazilian Software Process - Melhoria do Processo de Software Brasileiro) – as simplify the project plan and assist to the results and/or expected practices.
The paper approaches the Integrated Management tool, which favors projects that were developed collaboratively, helping to eliminate redundancy documents and the use of several tools, reduce the amount of papers, the loss caused by inefficient allocation of resources and the duplication in projects.
The initial version of the tool attend to ten PMBOK (Project Management Body of Knowledge) knowledge areas through integrated functionalities and templates and provide all the expected results for the MPS.Br Project Management process. This version was evolved and added new features, such as integrated Project Model Canvas environment and with the automatic generation of PMBOK templates.
The initial version of the Integrated Management was used to support projects management kept by the Brazil's Ministry of Education (MEC) and Ministry of Communications (MC). The evolved version of the tool was the winner of the 2013's Best Project of the Year in the category Innovative Project, published by the World Project Management magazine. Currently, the tool also provides the Project Model Canvas functionality for smart boards, using features such as virtual reality and simulators to increase the use of visual models in order to improve the interaction among stakeholders and in the project plan design.
This paper is organized in the following sections: section II shows a comparative between the project management process presents in the maturity models for software (CMMI e MPS.Br) and the PMBOK knowledge areas; in the section III is discussed the Project Model Canvas methodology; the section IV proposes how Project Model Canvas can assist at the design of a project plan, meeting the expected results of MPS.Br and the CMMI specifics practices, in regard to Project Management Software; the section V has the objective to show the Project Management tool called Integrated Management that supports the use of the Project Model Canvas; and the section VI presents the final thoughts of this paper.
II. PROJECT MANAGEMENT IN CMMI E MPS.BR
The Project Management is the application of knowledge, skills, tools and techniques to project activities in order to achieve their goals. Best practices are addressed through the PMBOK guide, where project management is divided into five process groups (initiating, planning, executing, monitoring and controlling, and closing) and includes ten areas of knowledge such as: integration, scope, time, cost, quality, human resources, risk, communication, procurement and stakeholders [1].
In this paper will be aborted the MPS.Br (Improvement of Brazilian Software Process) level G process called Project Management (GPR), equivalent to Project Planning (PP) and Project Monitoring and Control (PMC) processes, both from maturity level 2 of CMMI (Capability Maturity Model® Integration).
According to the MPS.Br General Guide, the purpose of the Project Management process (GPR) is establish and keep plans that define the activities, resources and responsibilities of the project [2]. According to the CMMI Technical Report, the purpose of Project Planning (PP) is to establish and maintain plans that define project activities and of Project Monitoring and Control (PMC) is to provide an understanding of the project progress so that appropriate corrective actions can be taken when the project performance deviates significantly from the plan [3].
The Table 1 shows the relationship between MPS.Br (expected results of the GPR level G process), CMMI (PP and PMC specific process pactices (SP)) and the PMBOK knowledge areas.
TABLE 1. MPS.Br (GPR) X CMMI (PP e PMC) X PMBOK
MPS.Br (GPR)	CMMI (PP e PMC)	PMBOK
GPR1 – Scope Definition	PP - SP 1.1 Estimate the Scope of the Project	Integration and Scope
GPR2 – Scaling Task	PP - SP 1.2 Establish Estimates of Work Product and Task Attributes	Time and Scope
GPR3 – Model definition and lifecycle phases	PP - SP 1.3 Define Project Lifecycle Phases	Integration and Scope
GPR4 - Estimates of cost and effort	PP - SP 1.4 Estimate Effort and Cost	Time, HR and Costs
GPR5- Budget and Schedule preparation	PP - SP 2.1 Establish the Budget and Schedule	Costs and Time
GPR6 – Definition of risks, impacts, probabilities and treatment priority	PP - SP 2.2 Identify Project Risks	Risk
GPR7 – Human Resources Planning	PP - SP 2.4 Plan the Project Resources	HR and Stakeholders
GPR8 - Planning of resources and working environment	PP - SP 2.4 Plan the Project’s Resources	Integration, Scope and Procurements
GPR9 – Identification of information, planning the collection, storage and distribution	PP - SP 2.3 Plan Data Management / PP - SP 2.5 Plan Needed Knowledge and Skills	Communication
GPR10 - Preparation of the project implementation plan	PP - SP 2.3 Plan Data Management / PP - SP 2.7 Establish the Project Plan	Integration
GPR11 - Assessment of the availability of achieving the goals	PP - SP 3.1 Review Plans That Affect the Project / PP - SP 3.2 Reconcile Work and Resource Levels	Integration and Scope
GPR12 – Project Plan Reviews	PP - SP 3.1 Review Plans That Affect the Project / PP - SP 3.2 Reconcile Work and Resource Levels / PP - SP 3.3 Obtain Plan Commitment / PMC - SP 1.2 Monitor Commitments	Integration, Scope and Stakeholders
GPR13 - The Scope, tasks, estimations, budget and project schedule are monitored	PMC - SP 1.1 Monitor Project Planning Parameters	Scope, Time and Costs
GPR14 – The material and human resources and also the relevant project data are monitored	PMC - SP 1.4 Monitor Data Management	HR, Procurements and Stakeholders
GPR15 – The risks are monitored	PMC - SP 1.3 Monitor Project Risks	Risks
GPR16 – The stakeholders involved in the project are planned, monitored and stored.	PP - SP 2.6 Plan Stakeholder Involvement / PMC - SP 1.5 Monitor Stakeholder Involvement	Stakeholders
GPR17 – Reviews are made in projects milestones.	PMC - SP 1.6 Conduct Progress Reviews / PMC - SP 1.7 Conduct Milestone Reviews	Scope
GPR18 - Register the problems identified and the result of analysis of relevant issues are established and treated	PMC - SP 2.1 Analyze Issues	Risks, Quality and Communication
GPR19 - Actions to correct deviations from the planned and to prevent recurrent problems are established, implemented and monitored	PMC - SP 2.2 Take Corrective Action / PMC - SP 2.3 Manage Corrective Actions	Risks, Quality and Communication

III. PROJECT MODEL CANVAS
The project management plan documents the strategy that will be used to manage the project and the related process to the PMBOK knowledge areas, then a Project Plan must contain all necessary information for project execution. The Project Plan plays an integration function, ei it integrates all the individual management plans into an cohesive unit, creating a centered document to describe all the parts of the project. The Project Plan also includes the projects baselines (scope, schedule and costs).
The Project Plan is created after the Project Charter (PC), document containing the title, description, objectives, justifications, constraints, premises, stakeholders, project manager and all other necessary informations to authorize the beginning of the project. The Table 2 shows the main documents that make up the Project Management Plan according to the PMBOK guide.
 TABLE 2. PROJECT PLAN DOCUMENTS
Documento	Descrição
Project Organization	It has roles and responsibilities, consolidates informations about the stakeholders and their interests.
Scope Baseline	Project Scope Declaration (document that defines and details all the project deliverables); Work Breakdown Structure – WBS (hierarchical decomposition of project deliverables, supporting document for scope management); / WBS Dictionary.
Schedule Baseline	Schedule (schedule of tasks with their durations, dependencies and other information).
Costs Baseline	Budget (Costs and cash flow of the project).
Knowledge Areas Management Plan	Scope Management Plan, time, costs, quality, communication, human resources and staeholders, risks and procurements.
Requirements Management Plan	Defines how the requirements are reunited, analyzed, prioritized, managed and controlled.
Changes Management Plan	Defines how to manage the changes and the change process in the project.
Configuration Management Plan	Defines how to manage changes in the documentation about deliveries and project processes.
Process Improvement Plan	Defines how the processes that are used in the project are available and improved.

The main idea of the Model Project Canvas is to simplify the project plan through a visual model based on Business Model Generation, where the way to scratch a business is quite clear by visual stimuli that provide a quick and intuitive mental processing.
The Model Project Canvas is a fast way to design a project plan, its use is to design the project logic and allows mounting a mental model of it. The main motivation of this methodology is to provide for the people involved, the understanding of the relationships between design concepts. Through a canvas on A1 paper format are stuck post-its with short and objectives sentences in thirteen areas that divide the canvas and each area is grouped into groups of questions as follows (Figure 1) [5]:
- Why? This group tries to answer the real motivation to improve the situation in the implementation of the project aims to tackle. The areas are: Justifications, Smart Goals and Benefits;
- What? Any project is executed to generate some result, service or product. In this group, the focus is making explicit what is the "output" and its aspects after the project implementation. The areas are: Product and Requirements;
- Who? In previous areas we have idea of the current problem of the organization, in which level it wants to be in the future, which product will be obtained and its characteristics. So to get the expected results, the project is executed by people who influent the project directly or indirectly. So, the areas are: External Stakeholders and external factors, and Staff;
- How? This group responds to the question: how the work will be organized in the project? Product is a set of deliveries that are carried out by staff who contribute to the common good. Therefore, three areas make up the group to get a sense of the Premises, Shipping and Restrictions;
- When and How? When the project will be completed and how much will it cost? This question of the last group of the canvas will be answered by stucked post-its in these areas: Risks, Costs and Timeline.
Fig. 1. Project Model Canvas structure planning
The methodology of Project Model Canvas is divided as follows [5]:
- Conceive: at this stage are answered six fundamental questions (Who What Why How When and How???). Thus resulting in a specific order sequence;
- Integrate: this step ensures that consistency between the areas and sets up the integration between the components;
- Solve: this step identifies the points with problems (uncertainties, lack of information or contradictions) in the canvas elaboration;
- Report / share: the canvas will serve as a basis to generate other important documents for the project.
IV. PROJECT MODEL CANVAS ALIGNED TO SOFTWARE PROJECTS MANAGEMENT
The Project Model Canvas relates with the Project Charter and the Project Plan suggested by PMBOK, simplifying them through a visual map as illustrated in the Figure 2 [6].
Fig. 2. PMBoK x Project Model Canvas
Through an analyze in the Figure 2, it’s possible to establish a comparative between the areas of the canvas and the project management process in the CMMI and MPS.Br methodologies (regarding the expected results and/or practices related to project planning). This comparison is detailed in Figure 3.
Every canvas can be compared to GPR9 - Identification of information, planning the collection, storage and distribution (PP-SP2.5), since it can be utilized as a communication tool. Every canvas can be compared too, to a simplified project plan (GPR10/PP-SP2.3 e 2.7) and also represents any kind of revision in the project plan (GPR11 e 12/PP-SP3.1 a 3.3).

Fig. 3. Project Model Canvas x MPS.Br (GPR) e CMMI (PP)
V. INTEGRATED MANAGEMENT TOOL
This tool used Redmine as its initial platform, that is developed using the Ruby on Rails framework, its main characteristics are: open-source, provides an easy way to extend and custom configurations.
The characteristics aforementioned have facilitated the implantation of the tool and to do this, adaptations were elaborated through custom configurations, implementation of electronic formularies and specific plug-ins to obtain the functionalities.
The initial version of the tool has functionalities that attends PMBOK’s knowledge areas and the expected results of GPR from MPS.BR in the G level [7]. The second version has included functionalities as kanban (from Lean’s method) and process modeling [8] [9]. The latest version includes the Project Model Canvas’s functionality, that can be used in two ways: in a computer

A. Project Model Canvas (Computer Mode)

In the beginning of the tool’s development, it was noticed the methodology didn’t have an specific or own tool yet. This functionality is available as a plug-in linked to the Integrated Management Tool, as illustrated in Figure 4. or an intelligent board.

Fig. 4. Screen of the functionality Project Model Canvas (computer mode)
The user can add virtual post-its in a specific area from the canvas besides the possibility of drag and drop this from area to area. After the creation and acceptance of the Canvas’s project by the team involved in the project, the filled data through virtual post-its have to be reused in the creation and management of the documents from the project management area.
Therefore, the tool have mechanisms for the automated generation of artifacts using the data previous filled in the Canvas project, establishing a mapping of the informations generated in the Canvas and the functionalities covering the projects management’s areas as show the Table 3.
 TABLE 3. TEMPLATES AND CANVAS FROM THE TOOL
Canvas Fill	Available Templates
Justifications, Smart Goals, Benefits	Project Charter
Product, Requirements	Project Creation, Requirement's release
External Stakeholders, Teams	Project Charter, users and profiles registrations
Deliveries Group	Work Breakdown Structure (WBS)
Constraints, Assumptions	Project Charter
Risks	Risk Management Plan
Timeline	Work Breakdown Structure (WBS), Gantt
Costs	Budget

B. Project Model Canvas (Intelligent Board Mode)
In this mode the Project Model Canvas functionality occurs through use of intelligent board, where the components is manipulated through movements and touch in the board surface. This mode facilitates elaboration through project plan of interactive form and collaborative through participation of stakeholders in the meetings for project plan elaboration.
This mode the Project Model Canvas functionality provides the option of each participant send of your computer the post-its that they wish put in each canvas area. Project manager by dragging the P's icon for any canvas area opens one window with all post-its sent for that area at the discretion of the manager drag post-its that deems appropriate to canvas. Manager also can include new post-its in the canvas through of NP icon further those sent by meeting participants.
In the intelligent board also will appear icons representing users who are participating of the project plan elaboration and status each one. After closure of the project plan, it may be stored in the tool in computer mode, may be modified always that need. Therefore a project plan elaborate in the intelligent mode may be stored in the computer mode and a plan carried out in the computer mode may be open in the intelligent board mode, having total communication between modes.
The Figure 5 shows screen of the functionality in the intelligent board mode.
Fig. 5. Screen of the functionality Project Model Canvas (intelligent board mode)
VI. FINAL THOUGHTS
This paper concludes that the use of Project Model Canvas methodology brings benefits to the software project management through the project plan builded in a simple way, and collaboratively. The methodology adheres to the waited results or practices of the projects management from MPS.BR (GPR) and from CMMI (PP).
The Project Model Canvas functionality in the tool can turn the use of this methodology more efficient and productive in any kind of project, including software projects.
Since the start of the development of this functionality in a computer mode (2013, August), there wasn’t another tool that could automate the use of the methodology. In the intelligent board mode, as well as the automatic generation of templates for project management, these functions are considered unpublished until now.
References
[1]	PMI - Project Management Institute. A Guide to the Project Management Body of Knowledge – PMBoK. 5º Edição. EUA, 2013.
[2]	SOFTEX - Associação Para Promoção da Excelência do Software Brasileiro. MPS.Br – Guia Geral: 2012. Disponível em http://www.softex.br/mpsbr/_guias/guias/MPS.BR_Guia_Geral_2012.pdf.
[3]	SEI – Software Engineering Institute. CMMI® for Development, Version 1.3. Technical Report. Carnegie Mellon, 2010.
[4]	Mulcahy's, R. Preparatório para o Exame de PMP. 8º Edição. RMC, EUA, 2013.
[5]	Finocchio Junior, J. Project Model Canvas. Ed.Campus. 2013.
[6]	Abdollahyan, F. Seção “Especialista Responde”. Revista Mundo Project Management. Edição Ago/Set, 2013.
[7]	Silva, S. V., Coutinho, L. J., Vasconcelos, A. P. V. de, Barbosa, C., Reis, M., Leite, R., Barroso, L. “Gestão Integrada – Uma Ferramenta para Atender aos Processos de Gerência de Projetos e Portfólio do MPS.Br”. IV Workshop de Gerenciamento de Projetos de Software (WPGS 2011). SBQS 2011. Curitiba, 2011.
[8]	Silva, S. V. ; Barroso, L. ; Paulino, E. “Uma Ferramenta para Integração e Melhoria do Processo de Gerência de Projetos”. VI Workshop de Gerenciamento de Projetos de Software (WSGP 2013). SBQS 2013. Salvador, 2013.
[9]	Valle, M. J. ; Motta, R. ; Barroso, L. ; Silva, S. V. “Análise da Metodologia Lean - Kanban em Relação ao Nível G do MPS.Br”. Workshop Anual do MPS.Br (WAMPS 2013). Campinas, 2013.